## Title
Cody Adams
Matt June
Reynould Houle
CSC 383
Fall 2008
Homework
Assignment 10

## Project Schedule
| Start Date | Days Completed | Remaining Days
Tasks
Accelerator pedal | 2008-11-23 | 0 | 35
Brake pedal | 2008-12-28 | 0 | 35
Gear shifter | 2009-02-01 | 0 | 35
Steering Wheel | 2009-03-08 | 0 | 35
Feedback Module | 2009-04-12 | 0 | 160
Physics calculator | 2009-09-19 | 0 | 182
Map database | 2010-03-20 | 0 | 42
Environmental conditions database | 2010-05-01 | 0 | 20
Driver profile database | 2010-05-21 | 0 | 15
Map select menu | 2010-06-05 | 0 | 14
Scenario select menu | 2010-06-19 | 0 | 14
Dash display | 2010-07-03 | 0 | 35
Speakers | 2010-08-07 | 0 | 21
Windshield display | 2010-08-28 | 0 | 21
Instructor display | 2010-09-18 | 0 | 21
| Total Weeks: |  | 91
Formulas:
Start Date = SUM([Start Date, row above],[Remaining Days, row above])