## Project Schedule
Tasks | Weight | Start Date | Days Completed | Remaining Days
Documentation | 16% | 2010-01-22 | 60 | 13.44
Specifications | 17% | 2010-02-04 10:34 | 46.56 | 14.28
Code | 24% | 2010-02-18 17:17 | 32.28 | 20.16
Hardware Integration | 1% | 2010-03-10 21:07 | 12.12 | 0.84
Testing/Fixing | 21% | 2010-03-11 17:17 | 11.28 | 17.64
Delivery Prep/Polishing | 21% | 2010-03-23 | 0 | 17.64
| Total Weeks: |  |  | 12
100%
Formulas:
Days Completed = TODAY() - [Start Date]
Days Completed = TODAY()-[Start Date]
Start Date = SUM([Start Date, row above],[Remaining Days, row above])