## Project Schedule
Tasks | Weight | Start Date | Days Completed | Remaining Days
Food Item Entry Screen | 25% | 2010-03-16 | 7 | 8.75
Browse Food Screen | 25% | 2010-03-24 18:00 | -1.75 | 8.75
Manage Meal / Shopping List | 25% | 2010-04-02 12:00 | -10.5 | 8.75
*-- System Preferences | 25% | 2010-04-11 06:00 | -19.25 | 8.75
| Total Weeks: |  |  | 5
100%
Formulas:
Days Completed = TODAY() - [Start Date]
Days Completed = TODAY()-[Start Date]
Start Date = SUM([Start Date, row above],[Remaining Days, row above])

## Details
| Section Title | Status | % Complete
Food Item Entry Screen |  |  | 80
| Scanner gets data properly |  | 95
| Data matched to UPC dB |  | 80
| Quantity Increased in Food Inventory dB |  | 100
| Add New Food to UPC dB |  | 70
Browse Food Screen |  |  | 65 | Done
| Browse In-Stock and Depleted Inventory Seperately |  | 100 | In Progress
| Quick-Add to Meal / Shopping List |  | 20 | Not Started
| Food Item Details Screen / Add to Meal / List |  |  | On Hold
| *-- Find Recipes |  | 50
Manage Meal / Shopping List |  |  | 90
| Per-Item Edit |  | 100
| Clear |  | 100
| Print |  | 0
*-- System Preferences
Language
Units of Measure
Background Color