## Project Schedule
Tasks | Weight | Start Date | Days Completed | Remaining Days
SDD Artifact Creation | 20% | 2010-03-16 | 14 | 0
SRS (Working Final) | 20% | 2010-03-23 | 7 | 0
SDD (Working Final) | 20% | 2010-03-30 | 0 | 7
Working Final | 20% | 2010-04-06 | -7 | 7
FINAL PRESENTATION | 20% | 2010-04-13 | -14 | 7
| Total Weeks: |  |  | 3
100%
Formulas:
Days Completed = TODAY() - [Start Date]
Days Completed = TODAY()-[Start Date]
Start Date = SUM([Start Date, row above],[Remaining Days, row above])